## Group Member
Group Member | Role
abdellah mallek | Backend
bassam | Frontend
maha al-zaaim | Team Management & Project Coordination
hisham | Testing

## Project Overview
Project Name | Gym & Workout Tracker System
Objective | To develop a web/mobile system that allows users to track workouts, exercises, progress, and fitness goals.
Scope | User registration/login, workout logging, exercise database, progress tracking, dashboard reports.
Methodology | Agile (Scrum)
Project Duration | 8 Weeks

## Timeline
Week | Activities
Week 1 | Project planning, requirement gathering, define system features
Week 2 | System analysis and UML diagrams (Use case, Class diagram)
Week 3 | Database design and backend setup
Week 4 | Backend development (APIs, authentication, workout logic)
Week 5 | Frontend design (UI for dashboard, workout pages)
Week 6 | Integration between frontend and backend
Week 7 | System testing, bug fixing, performance improvement
Week 8 | Final documentation, report writing, and presentation preparation

## Budget Planning
Resource Type | Description | Estimated Cost ($)
Human Resource | 4 Members - 8 Weeks (Development & Management) | 2400
Software Tools | Development tools, hosting, database services | 400
Testing & Documentation | Reports, materials, printing | 150
Total Estimated Budget |  | 2950